## Blad1
Category | Sub-Category | Item Naam | Code | Prioriteit | Maker | DickPoints | Begin Datum | Eind Datum | Done | Time Spended
Concept Art | Concept Art
| Levels |  | 1CA_LE
|  | GrasLevel | CA_LE_GL
| Character |  | 1CA_CH
|  | Nina | CA_CH_NN
| Props |  | 1CA_PR
|  | Wooden Sword | 1CA_PR_WS
2D Art | 2D Art
| Textures |  | 2D_TX
|  | Ground | 2D_TX_G | 1 | Ruben | 1 | 2015-11-02 | 2015-11-06
|  | Gras Wall | 2D_TX_GW | 1 | Ruben | 2 | 2015-11-02 | 2015-11-06
|  | Tree Stump | 2D_TX_TS | 1 | Ruben | 4 | 2015-11-02 | 2015-11-06
|  | Sand | 2D_TX_SA | 1 | Ruben | 1 | 2015-11-09 | 2015-11-13
|  | SandBox | 2D_TX_SB | 1 | Ruben | 1 | 2015-11-09 | 2015-11-13
|  | WaterPool | 2D_TX_WP | 1 | Ruben | 2 | 2015-11-09 | 2015-11-13
|  | DolHouse | 2D_TX_DH | 2 | Kilian | 3
|  | Barn | 2D_TX_B | 1 | Ruben | 3 | 2015-11-09 | 2015-11-13
|  | SpiderWeb | 2D_TX_SW | 3 | Jesse | 2
|  | Grass | 2D_TX_GS | 3 | Ruben | 2
|  | Stone | 2D_TX_S | 3 | Kilian | 1 | 2015-11-16 | 2015-11-20
|  | SugerCube | 2D_TX_SC | 2 | Kilian | 1 | 2015-11-09 | 2015-11-13
|  | PlatenStaak | 2D_TX_PS | 1 | Jesse | 3 | 2015-11-16 | 2015-11-20
|  | Daisies | 2D_TX_D | 2 | Jesse | 2 | 2015-11-16 | 2015-11-20
|  | Needle | 2D_TX_N | 1 | Jesse | 3 | 2015-11-16 | 2015-11-20
|  | Spring | 2D_TX_SPR | 1 | Ruben | 1 | 2015-11-16 | 2015-11-20
|  | WoodenSword | 2D_TX_WS | 1 | Kilian | 2 | 2015-11-02 | 2015-11-06
|  | ButtonShield | 2D_TX_BS | 1 | Kilian | 2 | 2015-11-02 | 2015-11-06
|  | Wooden Platform | 2D_TX_WP | 3 | Ruben | 1
|  | Ant 1 | 2D_TX_A1 | 1 | Kilian | 4 | 2015-11-02 | 2015-11-06
|  | Ant 2 | 2D_TX_A2 | 2 | Kilian | 1 | 2015-11-09 | 2015-11-13
|  | Ant 3 | 2D_TX_A3 | 3 | Kilian | 1
|  | Nina | 2D_TX_NN | 1 | Jesse | 5 | 2015-11-02 | 2015-11-06
|  | Shovel | 2D_TX_SH | 2 | Kilian | 1 | 2015-11-09 | 2015-11-13
|  | Rake | 2D_TX_RA | 2 | Kilian | 1 | 2015-11-09 | 2015-11-13
|  | Sand Mold | 2D_TX_SM | 3 | Kilian | 1 | 16-now | 2015-11-20
|  | Leaves | 2D_TX_LE | 2 | Ruben | 2
|  | Chair | 2D_TX_CH | 3 | Jesse | 2
|  | CoatReck | 2D_TX_CR | 3 | Jesse | 1
|  | Stairs | 2D_TX_ST | 3 | Ruben | 2
|  | Dragonfly | 2D_TX_DF | 2 | Kilian | 4 | 2015-11-16 | 2015-11-20
|  | Mini Ray | 2D_TX_MR | 1 | Ruben | 4 | 2015-11-16 | 2015-11-20
|  | Table | 2D_TX_T | 1 | Kilian | 2 | 2015-11-09 | 2015-11-13
|  | TL Light | 2D_TX_TL | 3 | Jesse | 1
|  | Lightstaber | 2D_TX_LS | 3 | Jesse | 3
|  | Poison Bottle | 2D_TX_PB | 2 | Kilian | 2 | 2015-11-16 | 2015-11-20
|  | Bottle Cap | 2D_TX_BC | 2 | Kilian | 2 | 2015-11-16 | 2015-11-20
|  | Daddylegs | 2D_TX_DL | 1 | Kilian | 3
|  | Bucket | 2D_TX_BU | 3 | Kilian | 1 | 2015-11-16 | 2015-11-20
|  | Doll Pieces | 2D_TX_DP
|  | Water Sand Platform | 2D_TX_WSP
|  | Spider Boss | 2D_TX_SB
| HUD |  | 2D_HUD
|  | Full Heart | 2D_HUD_FH | 1 | Jesse | 1 | 2015-11-16 | 2015-11-20
|  | Half Heart | 2D_HUD_HH | 1 | Jesse | 1 | 2015-11-16 | 2015-11-20
|  | Stamina Bar | 2D_HUD_SB | 3 | Jesse | 1
|  | Tekst Could | 2D_HUD_TC | 3 | Jesse | 1
|  | Breath Bar | 2D_HUD_BB | 3 | jesse | 1
|  | Menu | 2D_HUD_MM | 1 | Kilian | 3 | 2015-11-09 | 2015-11-13
|  | Game Over | 2D_HUD_GO | 1 | Ruben | 2 | 2015-11-16 | 2015-11-02
|  | Intro Comic | 2D_HUD_IC | 1 | ?
|  | Pause Screen | 2D_HUD_PS | 1 | jesse | 1 | 2015-11-16 | 2015-11-20
|  | SkillTree Hud | 2D_HUD_STH |  | Jesse
|  | Crafting Hud | 2D_HUD_CH |  | Jesse
|  | Daisies Shield | 2D_HUD_DS | 3 | Jesse | 2
| Sprites |  | 2D_SP
3D Art | 3D Art
| Environment |  | 3D_E
|  | Ground | 3D_E_G | 1 | Ruben | 2 | 2015-09-14 | 2015-09-18 |  | 6
|  | Grass Wall | 3D_E_GW | 1 | Ruben | 1 | 2015-09-14 | 2015-09-18 |  | 2
|  | Sand | 3D_E_SA | 1 | Ruben | 2 | 2015-09-14 | 2015-09-18 |  | 3
|  | SandBox | 3D_E_SB | 1 | Ruben | 2 |  | 2015-10-26 |  | 4
|  | WaterPool | 3D_E_WP | 1 | Ruben | 1 | 2015-09-28 | 2015-10-02 |  | 4
|  | Barn | 3D_E_B | 1 | Ruben | 3 | 2015-10-05 | 2015-10-09 |  | 6
|  | Skybox | 3D_E_SK | 3 | Ruben | 1 | 2015-10-12 | 2015-10-16 |  | 1
| Main Character |  | 3D_MC
|  | Nina | 3D_MC_NN | 1 | Jesse | 5 | 2015-09-14 | 2015-09-25 |  | 30
| Npc's |  | 3D_NP
|  | DragonFly | 3D_NP_DF | 2 | Kilian | 3 | 2015-10-05 | 2015-10-09 |  | 6
| Buildings |  | 3D_B
|  | Tree Stump | 3D_B_TS | 1 | Ruben | 5 | 2015-09-21 | 2015-09-25 |  | 12
|  | Doll House | 3D_B_DH | 2 | Kilian | 4 | 2015-09-28 | 2015-10-02 |  | 8
| Props |  | 3D_P
|  | SpiderWeb | 3D_P_SW | 3 | Jesse | 2 | 2015-10-05 | 2015-10-09 |  | 1
|  | Grass | 3D_P_GS | 3 | Ruben | 1 | 2015-10-12 | 2015-10-16 |  | 1
|  | Stone | 3D_P_S | 3 | Kilian | 1 |  | 2015-10-26 |  | 1
|  | SugerCube | 3D_P_SC | 2 | Kilian | 1 | 2015-10-12 | 2015-10-16 |  | 1
|  | PlatenStaak | 3D_P_PS | 1 | Jesse | 3 | 2015-10-12 | 2015-10-16 |  | 15
|  | Daisies | 3D_P_D | 2 | Jesse | 2 | 2015-09-28 | 2015-10-02 |  | 1
|  | Needle | 3D_P_N | 1 | Jesse | 2 | 2015-09-28 | 2015-10-02 |  | 1
|  | Spring | 3D_P_SPR | 1 | Ruben | 1 | 2015-10-05 | 2015-10-09 |  | 1
|  | WoodenSword | 3D_P_WS | 1 | Kilian | 2 | 2015-09-21 | 2015-09-25 |  | 1
|  | ButtonShield | 3D_P_BS | 1 | Kilian | 2 | 2015-09-21 | 2015-09-25 |  | 1
|  | Wooden Platform | 3D_P_WP | 3 | Ruben | 1 |  | 2015-10-26 |  | 1
|  | Shovel | 3D_P_SH | 2 | Kilian | 2 | 2015-10-12 | 2015-10-16 |  | 1
|  | Rake | 3D_P_RA | 2 | Kilian | 2 | 2015-10-12 | 2015-10-16 |  | 2
|  | Sand Mold | 3D_P_SM | 3 | Kilian | 1 |  | 2015-10-26 |  | 1
|  | Leaves | 3D_P_LE | 2 | Ruben | 1 | 2015-10-05 | 2015-10-09 |  | 1
|  | Chair | 3D_P_CH | 3 | Jesse | 2 | 2015-10-05 | 2015-10-09 |  | 2
|  | CoatReck | 3D_P_CR | 3 | Jesse | 1 | 2015-10-05 | 2015-10-09 |  | 2
|  | Stairs | 3D_P_ST | 3 | Ruben | 1 | 2015-10-12 | 2015-10-16 |  | 1
|  | Mini Ray | 3D_P_MR | 1 | Ruben | 4 | 2015-10-05 | 2015-10-09 |  | 14
|  | Table | 3D_P_T | 1 | Kilian | 1 | 2015-09-28 | 2015-10-02 |  | 1
|  | TL Light | 3D_P_TL | 3 | Jesse | 1 | 2015-10-12 | 2015-10-16 |  | 1
|  | Lightstaber | 3D_P_LS | 3 | Jesse | 3 |  | 2015-10-26 |  | 2
|  | Poison Bottle | 3D_P_PB | 2 | Kilian | 2 | 2015-10-05 | 2015-10-09 |  | 1
|  | Bottle Cap | 3D_P_BC | 2 | Kilian | 2 | 2015-10-05 | 2015-10-09 |  | 1
|  | Daddylegs | 3D_P_DL | 1 | Kilian | 3 | 2015-09-21 | 2015-09-25 |  | 4
|  | Bucket | 3D_P_BU | 3 | Kilian | 2 |  | 2015-10-26 |  | 1
|  | Spider Boss | 3D_P_SB
|  | Doll Pieces | 3D_P_DP
|  | Seed | 3D_P_SD |  | Kilian
|  | Water Sand Platform | 3D_P_WSP
| Enemy's |  | 3D_E
|  | Ant | 3D_E_A | 1 | Kilian | 5 | 2015-09-14 | 2015-09-18 |  | 10
Unwraps | Unwrap
| Main Character |  | 4UW_MC
|  | Nina | 4UW_MC_NN | 1 | Jesse | 5
| Npc's |  | 4UW_NP
|  | DragonFly | 4UW_NP_DF | 2 | Kilean | 5
| Environment |  | 4UW_E
|  | Ground | 4UW_E_G | 1 | Ruben | 1
|  | Gras Wall | 4UW_E_GW | 1 | Ruben | 1
|  | Tree Stump | 4UW_E_TS | 1 | Ruben | 1
|  | Sand | 4UW_E_SA | 1 | Ruben | 1 | 2015-11-09 | 2015-11-13
|  | SandBox | 4UW_E_SB | 1 | Ruben | 1 | 2015-11-09 | 2015-11-13
|  | WaterPool | 4UW_E_WP | 1 | Ruben | 3 | 2015-11-09 | 2015-11-13
|  | Skybox | 4UW_E_SK | 3 | Ruben | 1
| Buildings |  | 4UW_B
|  | Tree Stump | 4UW_B_TS | 1 | Ruben | 4
|  | Doll House | 4UW_B_DH | 2 | Kilian | 4
| Props |  | 4UW_P
|  | SpiderWeb | 4UW_P_SW | 3 | Jesse | 1
|  | Grass | 4UW_P_GS | 3 | Ruben | 1
|  | Stone | 4UW_P_S | 3 | Kilian | 2 | 16-now | 2015-11-20
|  | SugerCube | 4UW_P_SC | 2 | Kilian | 1 | 2015-11-09 | 2015-11-13
|  | PlatenStaak | 4UW_P_PS | 1 | Jesse | 2
|  | Daisies | 4UW_P_D | 2 | Jesse | 2
|  | Needle | 4UW_P_N | 1 | Jesse | 2
|  | Spring | 4UW_P_SPR | 1 | Ruben | 1 | 2015-11-16 | 2015-11-20
|  | WoodenSword | 4UW_P_WS | 1 | Kilian | 2 | 2015-11-02 | 2015-11-06
|  | ButtonShield | 4UW_P_BS | 1 | Kilian | 3 | 2015-11-02 | 2015-11-06
|  | Wooden Platform | 4UW_P_WP | 3 | Ruben | 1
|  | Shovel | 4UW_P_SH | 2 | Kilian | 3 | 2015-11-09 | 2015-11-13
|  | Rake | 4UW_P_RA | 2 | Kilian | 3 | 2015-11-09 | 2015-11-13
|  | Sand Mold | 4UW_P_SM | 3 | Kilian | 2 | 2015-11-16 | 2015-11-20
|  | Leaves | 4UW_P_LE | 2 | Ruben | 1
|  | Chair | 4UW_P_CH | 3 | Jesse | 1
|  | CoatReck | 4UW_P_CR | 3 | Jesse | 1
|  | Stairs | 4UW_P_ST | 3 | Ruben | 1
|  | Mini Ray | 4UW_P_MR | 1 | Ruben | 5 | 2015-11-16 | 2015-11-20
|  | Table | 4UW_P_T | 3 | Kilian | 2
|  | TL Light | 4UW_P_TL | 2 | Jesse | 1
|  | Lightstaber | 4UW_P_LS | 3 | Jesse | 3
|  | Poison Bottle | 4UW_P_PB | 2 | Kilian | 2 | 2015-11-09 | 2015-11-13
|  | Bottle Cap | 4UW_P_BC | 2 | Kilian | 2 | 2015-11-09 | 2015-11-13
|  | Daddylegs | 4UW_P_DL | 1 | Ruben | 3
|  | Bucket | 4UW_P_BU | 3 | Kilian | 2 | 2015-11-16 | 2015-11-20
|  | Water Sand Platform | 4UE_P_WSP
| Enemy's |  | 4UW_EN_A
|  | Ant | 4UW_EN_A | 1 | Kilian | 5 | 2015-11-02 | 2015-11-06
|  | Spider Boss | 4UW_EN_SB
Rigging | Rigging
| Main Character |  | 5R_MC
|  | Nina | 5r_MC_NN | 1 | Jesse | 5 | 2015-11-09 | 2015-11-13
| Npc's |  | 5R_NP
|  | DragonFLy | 5R_NP_DF | 3 | Kilian | 4 | 16-now | 2015-11-20
| Enemy's |  | 5R_EN
|  | Ant | 5R_EN_A | 1 | Kilian | 5
Animaties | Animation
| Main Character |  | A6_MC
|  | Nina | A6_MC_NN | 1 | Jesse | 5 | 2015-11-09 | 2015-11-13
| Npc's |  | A6_NP
|  | DragonFly | A6_NP_DF | 3 | Kilian | 2
|  | SpiderWeb | A6_NP_SW | 3 | Jesse | 1
| Enemy's |  | A6_EN
|  | Ant | A6_EN_A | 2 | Ruben | 5
Sound | Sound
| Main Character |  | 7S_MC
Nina Walk
Nina Run
Nina shield
Nina springer
Nina holding breath
Nina Being hit
Nina Attack
| Props |  | 7S_NP
SugerCubes
Collectlebles
SpiderWeb
Leaves on water
Mina Ray Sounds
| Enemy's |  | 7S_EN
Ant Lopen
Ant aanvallen
Ant gehit
Ant Sounds
Dragon Fly Sounds
| Level Design |  | 7S_LD
Background Music
Water
Poison
Scripts | Scripts
| Adventure Gameplay |  | 8SC_AG
|  | Character Controller | 8SC_AG_CC | 1 | Harold
|  | Camara Controller | 8SC_AG_CCO | 1 | Alieke
|  | Health Player | 8SC_AG_HP | 1 | Alieke
|  | Fall Damage | 8SC_AG_FD | 2 | Mack
|  | Poison Death | 8SC_AG_PD | 3 | Mack
|  | Collecteble | 8SC_AG_CB | 3 | Alieke
|  | Interacting | 8SC_AG_I | 2 | Alieke
|  | Spawn/Checkpoint | 8SC_AG_SC | 2 | Mack
|  | Loading Screen | 8SC_AG_LS | 2 | Alieke
|  | Adam Inhouden | 8SC_AG_ADI | 3 | Harold
| H&S Gameplay |  | 8CS_HS
|  | Stamina | 8CS_HS_S | 2 | Mack
|  | Attack Player | 8CS_HS_AP | 1 | Alieke
|  | Attack Enemy | 8CS_HS_AE | 1 | Mack
|  | A.I Enemy | 8CS_HS_AIE | 2 | Harold
|  | Health Enemy | 8CS_HS_HE | 1 | Harold
|  | Defense Player | 8CS_HS_DP | 2 | Mack
|  | Enemy Spawner | 8CS_H_ES | 1 | Mack
| Puzzle Gameplay |  | 8CS_PG
|  | SpiderWeb | 8CS_PG_SW | 1 | Harold
|  | Water death | 8CS_PG_WD | 2 | Harold
|  | leaf moving | 8CS_PG_LS | 1 | Alieke
|  | Trigger Animation | 8CS_PG_TA | 3 | Alieke
| HUD |  | 8CS_HUD
|  | Health Bar | 8CS_HUD_HB | 1 | Harold
|  | Stamina Bar | 8CS_HUD_SB | 2 | Mack
|  | Madeliefjes Count | 8CS_HUD_MC | 3 | Alieke
|  | Denk Wolkje | 8CS_HUD_DW | 3 | Mack
|  | Menu Main | 8CS_HUD_MM | 1 | Mack
|  | Game Over | 8CS_HUD_GO | 2 | Alieke
|  | Game Pause | 8CS_HUD_GP | 2 | Alieke
|  | Comic Intro | 8CS_HUD_CI | 2 | Harold
|  | Comic Outro | 8CS_HUD_CO | 3 | Harold
| Extra |  | 8CS_EX
|  | Cheat Mode | 8CS_EX_CM | 2 | Harold
|  | Weapon Switch | 8CS_EX_WS | 1 | Harold
|  | Save/Load | 8CS_EX_SL | 1 | Mack
|  | Volume | 8CS_EX_V | 2 | Alieke
|  | Particals | 8CS_EX_P | 3 | Alieke
|  | Leveling System | 8CS_EX_LS | 2 | Mack
|  | Time Bonus | 8CS_EX_TB | 3 | Mack
|  | Weapon Effect | 8CS_EX_WE | 2 | Harold
|  | Crafting system | 8CS_EX_CS | 3 | Harold
Particals | Particals
| Npc's |  | 9P_NP
|  | Nina Jump | 9P_NP_NJ
|  | Nina Walk | 9P_NP_NW
| Props |  | 9P_P
|  | Pick Up | 9P_P_PU
|  | Shield Hit | 9P_P_SH
|  | Poison Bottle | 9P_EN_PB
|  | Crit Hit | 9P_P_CH
|  | Bleed Effect | 9P_P_BE
|  | Stun Hit | 9P_P_SH
|  | Shield Push | 9P_P_SP
|  | Leap Attack | 9P_P_LA
| Enemy's |  | 9P_EN
|  | Ant Hit | 9P_EN_AH
|  | Ant Bleeding | 9P_EN_AB
|  | Ant Stunned | 9P_EN_AS
|  | Ant Lopen | 9P_EN_AL
| Level Design |  | 9P_LD
|  | Water | 9P_LD_W
[5 empty] | 3D Art | 80 | 14 Per week | niet per persoon